## Project 3 Gantt
CIVE 202 ¦ Project #3 – VISUALIZE ¦ Gantt Chart
Michael Albracht |  |  |  | Project Start: Feb 26, 2026 | [14 empty] | Project End: Mar 31, 2026
TASK | START | END | PROGRESS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
MARCH 2026
Github Repository
Create Github Repo | 03/29 | 03/29 | 0%
Create README File | 03/29 | 03/30 | 0%
Upload Final Files | 03/30 | 03/30 | 0%
Submit to Canvas | 03/31 | 03/31 | 0%
Scope of Work
Identify Variables (NHTS/NGSIM) | 03/03 | 03/04 | 0%
Draft Scope Document | 03/20 | 03/22 | 0%
Data Cleaning & Processing
Clean NHTS Dataset | 03/05 | 03/07 | 0%
Clean NGSIM Dataset | 03/08 | 03/10 | 0%
Python Code Development
Create Bar Chart | 03/13 | 03/14 | 0%
Create Histogram | 03/15 | 03/16 | 0%
Create Boxplot | 03/17 | 03/18 | 0%
Create Time Series Plots | 03/19 | 03/22 | 0%
IDM Simulation Study | 03/23 | 03/27 | 0%
Technical Report
Analyze Code and findings | 03/20 | 03/23 | 0%
Write Introduction & Background | 03/24 | 03/25 | 0%
Write Methods Section | 03/25 | 03/26 | 0%
Write Results & Discussion | 03/26 | 03/28 | 0%
Write References & Finalize | 03/29 | 03/30 | 0%
Documentation
Annotated Code Document | 03/26 | 03/28 | 0%
Engineering Timesheet | 03/30 | 03/30 | 0%
LEGEND |  |  |  | Github Repository |  |  |  |  | Scope of Work |  |  |  |  | Data Cleaning |  |  |  |  | Python Dev |  |  |  |  | Technical Report |  |  |  |  | Documentation